## Sheet1
Source | Task | Estimate | Requirement | Note | Priority |  |  | Estimate
Strategy |  |  | Seperating user interfaces from core functionality
| Lamar is doing this (some is already done) | 1m | 1. Seperation of Instrument view from Mantidplot
| Investigate remaining links, expose to python | 1m | 2. Seperation of Visual fitting from Mantidplot | Might be done already?
SSC LowQ | Investigate and fix | 3m & ?3m | 3. Ensure all technique UI operations are not encoded into the UI
Dev meeting |  |  | 4. Code re-org
Dev meeting | High level reorg | 1m | top level to support better packaging (e.g. mantid, mantid-gui, ...)
Dev meeting | Reorg Framework code (decide what to do is hardest step) | 2m | inside framework still needs discussion
Dev meeting |  |  | improve speed of builds
Dev meeting |  |  | Properly isolating modules and tests so they can be run without the rest of the code base. This is the soft-link issue.
Dev meeting |  |  | More 'Concepts' in the code base co-located and properly separated. Not all geometry is in Geometry.
Strategy | Linux only | 1m | 5. Rework installers to support sub projects
Strategy | Decide what this means (some suggestions below) |  | Mantid as a SciPy styled python package
Dev meeting, Spectroscopy | Design and implement, estimate will vary based on sequqncing with workspace changes | 6-12m | 1. Improving the interface to access data and create workspaces in Python |  | H
Dev meeting |  |  | 1. CreateWorkspace is a particular problem, create a workspace in python, add the data you want and then register/save in mantid.
Dev meeting |  |  | 2. Workspaces should work with the minimum amount of data required
Dev meeting |  |  | 3. Tableworkspaces are very unpleasant.
Dev meeting |  |  | 4. Ensure cloning works nicely in python
Dev meeting |  |  | 5. Need to be able to add a limited instrument using just L2, theta (efixed) lists (Not for instrument view, just for unit conversion)
Dev meeting, SSC LowQ |  |  | 2. Defining a Core set of functions |  | L
Dev meeting | Define and separate | 3m | 1. define a core set of operations (Primarily maths + rebin, convert units)
Dev meeting | Separate expose and use | 3m | 2. Expose the looped operations to python directly (Note: these will not the the exact equivalent of the algorithm). | Timmy is keen on this, but it is not clear that others would use it.
Dev meeting | Ensuring everything is callable from C++ and python (in a pythonic way) | 6m | 3.changing framework from a python wrapped package to python package with c++ innards |  | L
Strategy |  |  | User centric documentation
Strategy | Improve alg documentation | 6m | 1. Document algorithms that cannot run on build servers
SSC Gen |  |  | General: maths and formulas are lacking, for example when they use the GSL for a spline.
SSC Gen |  |  | Put more (automated) information in the algorithms documentation pages: info from validators. For example if values need to be positive, if it only applies to some type of workspaces, etc. [FMP: Strong support and apparently consensus this is worth and doable] | Yes we should do this, as much as possible
| Improve concepts docs | 3m | 2. Expand documentation for non algorithm objects including documentation tests
SSC LowQ |  |  | Some of the fitting features are not well advertised. | Update training and docs
| SINE2020 Karl, plan and implement | 12-24m | 3. Better developer documentation
Strategy |  |  | Tested documentation for system setup for new developers
Dev meeting |  |  | Mantidplot design doc
Dev meeting |  |  | We are missing scientific technique overviews
Dev meeting |  |  | Missing some detailed design docs
Dev meeting |  |  | Exposing objects to python could do with more docs / easier to find
Dev meeting |  |  | What packages to use for what & examples, e.g. xml, json
Dev meeting |  |  | Algorithm options not well explained child/managed/unmanaged
Dev meeting |  |  | Create a chart explaining where things are in Mantid.
Dev meeting |  |  | Information available on the wiki, but not easy to find
Dev meeting |  |  | Go through and clean the wiki every release/maintenance task. | Add to recurring maintenance list
Dev meeting |  |  | Devs need permission to delete pages | To be done
Dev meeting |  |  | Feels like things related to development should be on the github wiki. | Decide location and stick to it, why add another location
Dev meeting |  |  | Guide for GUI development is not a guide for GUI development. | SINE 2020 effort
SSC Gen | Find, chase include | 1m | 4. Do something to integrate instrument specific documentation (like for example the SANS technique wiki pages. | Links to instrument created pages is a no-brainer
SSC Gen | Investigate better search options & implement | 3m | 5. Search: improve search (google, tags, meta-info). Keyworkds messed up (workspace group, group workspace). | This was suggested by dev team, but did not get much traction with SSC
Strategy |  |  | Extensible and flexible instrument geometry and units
Dev meeting | Underway | 16m+ | 1. Geometry redo
Dev meeting | plan and implement | 6-9m | 2. Units redo
Strategy | Plan agree and implement | 12m+ | Workspace types to more efficiently reflect the science
Dev meeting |  |  | 1. refactor workspace hierarchy
Dev meeting |  |  | 2. remove inheritance from Experimentinfo - move to owning a multiple experimentinfo (with ease of use for 1)
Dev meeting |  |  | 3. remove Mdworkspace inheritance links
Dev meeting |  |  | Do we have the correct base class ? (Probably not)
Dev meeting |  |  | Should some kind of data object be the place for variation (e.g. Histogram1D)
Strategy | Find an implement a use case requires a Instrument scientist to by a consumer | 3m | Experiment Steering
Dev meeting |  |  | The aim is to make Mantid unaware of experimental control. Mantid is a passive service to experimental control. Interaction the other way around does not yet make sense. Essentially this means we need to have the following.
Dev meeting |  |  | 1. Mantid needs to be made very stable so that it can reliably be used over long durations of an experiment.
Dev meeting |  |  | 2. Mantid needs to be made thoroughly pythonic so that we can glue it to the instrument control framework via python.
Dev meeting |  |  | 3. Geometry should be separable from the data reduction parts of Mantid
Dev meeting |  |  | 4. A headless distribution of Mantid may be an advantage
Strategy |  |  | Advanced Visualization
Strategy |  |  | Mantid connecting to advanced analysis and modelling
Strategy | Investigate, plan and implement basic | 6m | Utilization of distributed and heterogenous computing environments
Dev meeting | MD and other workspace | 12m | 1. MPI changes to algorithms
Dev meeting | Visualisation and interaction | 12m | change the algorithm base class
Dev meeting |  |  | re-write LoadEventNexus and other that need it
Dev meeting |  |  | re-write ConvertToMD
SSC Gen, SSC Spectroscopy |  |  | Stability |  | Very High
Dev meeting, SSC Spectroscopy | Make gui testable (MVP + unit or otherwise) | 2-3m per interface (10+) | 1. Refactoring user interfaces to improve testability | Sliceviewer MVC? VSI MVC? Indirect GUIs? Squish Tests? | High
SSC LowQ | Refactor scripts, update uis | 3m | Python scripts interfaces should be cleaned-up on the SANS side (both SNS and ISIS) | Internal cleanup, validation
Dev meeting |  |  | 2. Technical debt
Dev meeting |  | ongoing | Reduce size of algorithms' exec
Dev meeting |  | 3m | Property
Dev meeting |  | 1m | AlgorithmProxies (we no longer need them)
Dev meeting |  | 1m | Algorithms that depend on MantidPlot should be either re-written or moved out of Framework
Dev meeting |  |  | 3. Not enough effort put into testing, causes problems down-stream (To be discussed at Workshop)
Dev meeting | Done |  | Review process should be done via gatekeepers. | Introduced for R3.7+
Dev meeting |  |  | Triage step should be considered. But needs to work faster. Probably easy to implement via labels. | Alternate, each developer to push back poorly defined issues
SSC LowQ |  |  | 4. SNS feel like they would like to have better control of the versions of Mantid that they are using. Needs to be controllable by the beamline/instrument scientists. |  | Low
SSC LowQ |  |  | 5. Longer beta test period |  | Low
SSC Gen |  |  | User Experience
Dev meeting |  |  | 1. Improving Interoperability
Dev meeting |  |  | assist instrument scientists in getting data to/from mantid to other programs
Dev meeting |  |  | 2. algorithm naming and transitioning towards better
Dev meeting, SSC Gen |  |  | Too many available algorithms, few of them core, some duplicated, change insane names of algorithms (make..., create..., generate...) maybe by deprecating?
3. Communication
Dev meeting |  |  | Development group meetings to inform people that interesting stuff is being worked on. | development working group
Dev meeting |  |  | Should notify instrument scientists (a) when stuff has been scheduled (b) a running estimate on when it's going to be ready. | The only sensible way is via issues/PRs
Dev meeting |  |  | We need to have a live schedule communicated to the instrument scientists. This could be done per group. | Per group meetings and communication will be discussed
SSC Gen |  |  | 1 & 2D plotting
SSC Gen |  |  | Excel plots are easy but with Mantid I need to teach myself everytime (Joe Kelleher) Counterarguments: do we want full blown plots in Mantid? Is this our mission? | Nothing to do here?
SSC Gen |  |  | error bars: horizontal caps too big (Ron Smith and others). | Add control of error bar drawing, bring all error bar controls together
SSC Gen |  |  | plot every error bar | This is already possible with option, change default? Currently off
SSC Gen |  |  | is it possible to drag curve from one plot to another plot? Wanted: more drag&drop and intuitive visual feedback
SSC Gen |  |  | Graph management: yes, improvements would be nice, but priorities are: multiple scattering, etc. which should be the focus of Mantid. | This is a note rather than functionality
SSC Gen |  |  | With plots and graphs in general: nice to have simple "export to .txt" for loading in 3rd party tools. | Relatively simple to do for single line graphs, lots of questions for multi line plots.
SSC Gen |  |  | Waterfall plots, with multiple axes, and surfaces (lots of parallel discussions hard to track). | Need to compare and align with users expectations - Fill under plot etc. This is currently supported, but change defaults?
SSC Gen |  |  | Defaults for plots. There could be specific template or common plots that show up in right-click/context menu of workspaces when data comes from a particular instrument. Example: ENGIN-X, both detectors on color plots side-by-side. Have a mechanism to define templates and use them based on the instrument (from the IDF). Otherwise, they'll do their scripts for these plots but then the usability is poor. | Allow graphs to output python that defines it, use this in the save/load project mechanism as well.
SSC LowQ |  |  | Template library for graphs (4) | See above & implement a library
SSC Gen |  |  | Change the quantity that is plotted: ToF to dSpacing, etc., ToF to Energy (keeping track of conversions when you go back and forth). Demand from both ISIS and SNS. | This makes sense, ?use workspace underneath, or on the fly transformation.
SSC Gen |  |  | Slice Viewer + Instrument Viewer
SSC Gen |  |  | Non-orthogonal axes, like ParaView does. Pascal & Ross.
SSC Gen |  |  | Good defaults, as has been done for the VSI, capability to remember settings (including positions).
SSC Gen |  |  | General point about plots: link different plotting tools (3D view, SliveView, ?2D plots). Link the different views of the same data. This was one of the requirements from single crystal (Christina Hoffmann). Much emphasis from Garreth, Pascal, Christina. Note: in discussions next day, a "synchronize" button was seen as a good option, as you don't always want continuous, real-time sync between plots. | The greatest benefit was between 3D and slice viewer (with instrument view for peaks (but I think that is already done).
SSC Spectroscopy |  |  | Mslice – put together a specification evaluation, then evaluate existing (half done?) code | This needs to be picked up by someone and done. Does this reduce the needs of slicing in the slice viewer for this community.
SSC Gen |  |  | From previous point: adapted interfaces for ISIS-excitations. Deviate from the approach of providing a generic tool? There's also demand from SNS: something like MSlice (so you don't need to fill in so many boxes), but better because Mantid has crystallography information.
SSC Gen |  |  | Ross: cuts, they define them numerically, to batch-apply to different datasets, and they currently need to repeat tedious steps. | Implement mslice first, see if there is enough residual desire to make further changes to the sliceviewer
SSC Gen |  |  | It should be like MSlice (very simple overplots): ability to find the cut quickly and overplot the cuts quickly. | Implement mslice first, see if there are any general issues to learn for the sliceviewer
SSC Gen |  |  | SliceViewer 1D plotting: needs to be easier to use, "quicker feel". Ask the excitations group, those who use it. They don't feel comfortable with it. The feeling of the tool is not good, not quick as MSlice (they're happy with). With SliceViewer they are not happy, probably because MSlice is more adapted to specific needs of particular instruments.
SSC Gen |  |  | Fitting
SSC Gen |  |  | Joe Kelleher with strong support from many:
SSC Gen |  |  | doesn't remember parameters
SSC Gen |  |  | doesn't remember limits
SSC Gen |  |  | which line is the peak? Make more obvious that the lines can be dragged. | Make peaks start with a non zero width
SSC Gen |  |  | Expose statistics [FMP: I think this is covered by the largely unknown alg. CalculateChiSquare]
SSC Gen |  |  | Other ways of outputting how the fitting worked: a python dict, export HDF, etc. | The current table workspace is a nightmare to work with in python for this use case
SSC Gen |  |  | Sangamitra:
SSC Gen |  |  | fitting doesn't work for some conditions | Anders to approach for examples
SSC Gen |  |  | Sequential fitting
SSC Gen |  |  | You want to plot the output of the fits. Plot against run numbers, for example for muons (Steve Cottrell, Pascal) | This is better control of what you are fitting the summary data against.
SSC LowQ |  |  | Projects
SSC Gen |  |  | Save project, lots of demand. Takes long, it should not save files over and over. | Firstly add save/load functionality for all interfaces visualization types. Performance Options: 1. Partial Save functionality (select graphs / workspaces then only save what is needed) 2. Express Save - Only save History from a workspace since it was last loaded, then rerun on Load Project, then regenerate graphs 3. Complete Save (as currently)
SSC LowQ |  |  | Saved project files are too big. Would be good to have some control over what gets added to the project file. | see below
SSC LowQ |  |  | Would be good to extract a project from an individual plot. | see below
SSC Gen |  |  | Technique User Interfaces
SSC LowQ |  |  | A web front end to Mantid has universal support. Reduction does need to be redone sometimes and a web-based application would make this a lot easier. | Simple UI for SANS / Reflectometry reduction, ? Using autoreduction hardware | Medium
SSC LowQ |  |  | There was a general liking for technique specific web-based tools, over the general tick client Mantiplot.
Dev meeting |  |  | Web interfaces of the future, we need common design - Pilot
SSC Spectroscopy |  |  | Skins – i.e. different technique specific interfaces, even going so far as to hide Mantidplot (e.g. muon GUI is the only thing muon users need to see, at least initially). This would include sliceviewer | The future GUI approach, web vs standalone needs to be considered here before picking a direction here.
SSC LowQ |  |  | Training users to use MantidPlot is too complicated. Autoreduction has allowed that to be avoided.
Spectroscopy
SSC Spectroscopy |  |  | Multiple scattering corrections | Validation of existing routines, then next steps
SSC Spectroscopy |  |  | Multi phonon corrections – especially important for powders
SSC Spectroscopy |  |  | Multi-dimensional visualisation – needs to be made useable. Professionally developed user experience (UX) | Quote for UX help? Do the users actually know what they want?
SSC Spectroscopy |  |  | Resolution convolution of S(q,w) and fitting. Different approaches, of differing levels of sophistication, favoured by different groups. This could be done externally to Mantid (in Python) as a research project, before being integrated into the framework | Underway
SSC Muon |  |  | Muon spectroscopy – transverse field analysis needs to be finished, and GUI written | Underway
SSC Muon |  |  | Muon – global fits into the muon GUI (urgent)
SSC Spectroscopy |  |  | Complete VESUVIO transfer from VMS
SSC Spectroscopy |  |  | GUI <-> script, this should be made easier, i.e. should not be workflow that is only in the GUI and not in corresponding script | Add "Py" script output buttons to all dialogs
SSC Spectroscopy |  |  | Scientist-written Python routines preferred, to ensure flexible and rapid development of technique | This is always possible, ?nothing to do here
SSC Spectroscopy |  |  | Script repository – we like it, but documentation of scripts in there needs to be made easier. Also publicising needs to be possible (e.g. powder QE) | Consider, and porpose improvements
Low Q
SSC LowQ |  |  | Performance (1)
SSC LowQ |  |  | Speed with big event files is a problem. Stop flow type experiments. Maybe we can do something about this? | Steve King - For sample data, profile bottlenecks, actions based on results | High
SSC LowQ |  |  | For example, general feeling that a lot of SANS processing is reloading files several times. This should be optimized out. We should look at way to improve speed with some of these workflows. | ISIS SANS - Investigate and improve, can partial loading help here? | High
SSC LowQ |  |  | Batch Processing (2)
SSC LowQ |  |  | Batch processing is where SNS Sans is heading. Bulk processing needs to be addressed; a lot of time can be wasted on that. |  | High
SSC LowQ |  |  | Users at ISIS SANS2D getting to a point that that they don’t have enough hardware to do the reduction. |  | High
SSC LowQ |  |  | Event Filtering (5)
SSC LowQ |  |  | Event Filtering/Examination (Data Explorer) interface required for complex metadata. Set complex criteria for which events to select. All based on some parameter you track. The functionality to do the processing is probably in there. Would be useful for more than just one technique area. See similar interfaces for video editing. | Improve FilterEvents UI usability, lack of labels, poor gui design, better explanations.
SSC LowQ |  |  | Other Comments
SSC LowQ |  |  | Most groups have most of what they want. In a ‘evolutionary’ stage rather than a ‘revolutionary’ stage.
SSC LowQ |  |  | Processing 2D Detectors. Not possible for ISIS reflectometers. Should be possible with a little work.
SSC LowQ |  |  | Should be able to have rotated 2D detectors 45 degrees
SSC LowQ |  |  | Mantid doesn’t deal in units of single runs. MantidPlot doesn’t work well in this regard.
SSC LowQ |  |  | Lack of planning tools
SSC LowQ |  |  | Manual ‘house keeping’ labelling of runs is often required to achieve batch processing/autoreduction. | Work with DAS for better labelling
|  |  | Diffraction / SX / Engineering |  | Diffraction | Single Crystal | Engineering Diffraction
SSC Diffraction |  |  | Absorption & Multiple Scattering. Look at Alan's code (all) |  | 1 | 1 | 3
SSC Diffraction |  |  | Calibration |  | 1 | 1 | 1
SSC Diffraction |  |  | Usability of fitting: |  | 2 |  | 2
SSC Diffraction |  |  | * Single peak - Initial guesses based on instrument in non-TOF units (all)
SSC Diffraction |  |  | * Improved algorithms for different dspacing range, e.g. different shapes for different banks
SSC Diffraction |  |  | * Look at things done on e.g. SXD
SSC Diffraction |  |  | * Defined outputs based on instrument/technique
SSC Diffraction |  |  | * Batch fitting with functions, consider interface to GSAS (Pascal)
SSC Diffraction |  |  | Macro Molecular - Profile fitting (Leighton show stopper) |  |  | 2
SSC Diffraction |  |  | Work in detector coordinates (Pascal/Leighton) |  |  | 2
SSC Diffraction |  |  | Peak Integration for Non-Sphere shapes (all) |  |  | 3
SSC Diffraction |  |  | Non-rectangular detector geometry for calibration |  |  | 1
SSC Diffraction |  |  | Calibration from SCDCalibratePanels - Output is clunky (Leighton) |  |  | 1
SSC Diffraction |  |  | Documentation/Consistency for input parameters e.g. workspace index vs spectrum number (Ron) |  | 3 | 3 | 2
SSC Diffraction |  |  | Live data roll out acrosss more instruments (Kate) |  | sms 1: isisi 3 | sms 1: isisi 3 | sms 1: isisi 3
SSC Diffraction |  |  | Improved integration with 3rd party tools (Kate) |  | 2 | 2 | 1
SSC Diffraction |  |  | * Some things might just have to be ported. Emphasis on speed & improvements (Alan)
SSC Diffraction |  |  | Wavelength normalization (requires space group information) (scd) (Leighton). Not done on SXD |  |  | 10
SSC Diffraction |  |  | * Scale between orientations/detectors
SSC Diffraction |  |  | * LAUENORM software is used but very old and may become unusable at some point
SSC Diffraction |  |  | * Anvred correction does basic wavelength correction ~small molecules but not for macro molecules
SSC Diffraction |  |  | * Does spherical but needs general polyhedra (ANVRED3/GAUSSIAN3.1 do this) for absorption correction
SSC Diffraction |  |  | MD Normalization Integration to UI |  |  | 1
SSC Diffraction |  |  | Vates Usability Improvements (scd, Pascal) |  |  | 2
SSC Diffraction |  |  | * Python API improvements (scd)
SSC Diffraction |  |  | * Synchronization of plots |  |  | 0
SSC Diffraction |  |  | * Overlaying HKL and Q |  |  | 0
SSC Diffraction |  |  | Non-orthogonal axes in Slice Viewer. Done in SXD2001 (general, Pascal) |  |  | 1
SSC Diffraction |  |  | Waterfall plots for time-sliced data - usability and education |  | 2 |  | 2
SSC Diffraction |  |  | Total Scattering: |  | -2
SSC Diffraction |  |  | * Algorithm to run Gudrun and import data back in. Long term to give GUI (Helen)
SSC Diffraction |  |  | * SNS Event-based PDFGetN functionality in Mantid - incorporating quick options (Kate)
SSC Diffraction |  |  | * Careful about different language used for the same thing
SSC Diffraction |  |  | * Inelastic/incoherent corrections (Kate/Helen)
SSC Diffraction |  |  | * Cosmetic corrections. Things that make the FFT look better (Helen)
SSC Diffraction |  |  | Non-detector components in instrument geometry and linking to information from a run (Kate) |  | 3 | 3 | 3
SSC Diffraction |  |  | * tracking sample environment
SSC Diffraction |  |  | Masking (all)
SSC Diffraction |  |  | * A few more automatic mechanisms like masking by threshold etc |  | 3 | 3 | 3
SSC Diffraction |  |  | Multiple UBs (scd) |  |  | 1
SSC Diffraction |  |  | Engineering:
SSC Diffraction |  |  | * Inversed pole figures |  |  |  | 1
SSC Diffraction |  |  | * Call MAUD from Mantid |  |  |  | 3
SSC Diffraction |  |  | * Call GSAS repeatedly |  | 3 |  | 1
SSC Diffraction |  |  | Planning and data quality tools (all) |  |  | 2
SSC Diffraction |  |  | * chopper setting tool
Technical
1. Speed up builds
Dev meeting |  |  | Clang format tools resubmit after PR, can we have this automatically applied
Dev meeting |  |  | More build servers? Every facility should have at least one build server for the supported platform. | This is unacheivable for newer partners, we need a better way
Dev meeting |  |  | Run the system tests as a downstream job | If downstream job cancellation worked well this would help
Dev meeting |  |  | Shrink system tests | Not a fan of this, unless the whole collection runs nightly at least.
Dev meeting |  |  | Split system tests (split the system tests across the same jobs) | This could work
Dev meeting |  |  | VMs shared across all facilities. What is the cost of this. Create images for all the VMs. | Is the UK RH6 the same environment as the US RH6?
Dev meeting |  |  | 2. Faster unit test suites
Dev meeting |  |  | Start enforcing limits on the long-running tests should be checked at PR | Suggestion on checklist
Dev meeting |  |  | Maintenance tasks should be done to go through long-running tests | Add to maintenance list
Dev meeting |  |  | We need some way of logging spurious failing system/unit tests/doctests on master | Decide on approach
Dev meeting |  |  | 3. Larger list of historic PR packages. Really slows testing down when you have to build and package everything. Should keep packages until the PR is closed.
Dev meeting |  |  | We need to pay for more space, or find ways to host these somewhere else. Would definitely be worth doing. | TSC: Look into what is needed here this could be a real time saver
Dev meeting |  |  | Alternative is to have a manual job to create one-off packages based on a PR and platform | This is an alternate approach, but much slower, breaks the thread
Comments from dev meeting - not tasks to do
Dev meeting |  |  | Nexus file and logs "are a real nightmare"
Dev meeting |  |  | Mantid shields many devs from this
Dev meeting |  |  | No real experince of this in group
Dev meeting |  |  | Not everything we will have to work is perfect
Dev meeting |  |  | Some cans of worms should remain unopened
Dev meeting |  |  | Hard to find history after the code reorganisation
Dev meeting |  |  | Reorganise code less often
Dev meeting |  |  | Some custom interfaces are too hard to maintain. How can we correct this?
Dev meeting |  |  | Front end complexity, consider refactoring, consider a simpler interface (in addition)
Dev meeting |  |  | Back end complexity - refactor
Dev meeting |  |  | MantidPlot described as a horror, but a "mature/polished/bug-fixed horror"
Dev meeting |  |  | The prime example of a missing design doc
Dev meeting |  |  | Is possible to extend, but the original design is too rigid
Dev meeting |  |  | Some of the worst examples of classes that are too long
Dev meeting |  |  | Not worth complete redesign for a 2nd choice tool of the future
Dev meeting |  |  | Future interfaces / gui aspects should be designed as widgets for use elsewhere as well
Dev meeting |  |  | Developer documentation is low-quality
Dev meeting |  |  | Induction material is fine
Dev meeting |  |  | Architectural design doc ok at a high level
Dev meeting |  |  | Development processes is fine
Dev meeting |  |  | We could use some examples of model Mantid code to help new developers (and old-hands too)
Dev meeting |  |  | See suggestion in dev documentation
Dev meeting |  |  | Excessive use of Singletons
Dev meeting |  |  | Stop using them | Design guidelines?
Dev meeting |  |  | Fitting of anything other than 1D too hard to use - look to see how it is done in scipy as a sample interface
Dev meeting |  |  | Adding new property types is too hard
Dev meeting |  |  | See Owen's notes from Tuesday afternoon
Dev meeting |  |  | 11) Macros for git commands
Dev meeting |  |  | Working on forks may be made easier. Particularly pulling from another developers branch on their fork.
Dev meeting |  |  | This group is not entirely convinced of the value. | Educate developers on GIT, remove the crutch
Dev meeting |  |  | 10) More spontaneous communication between facilities
Dev meeting |  |  | Create more channels on Slack. | ?will more channels improve communication?